## Sheet1
I. Strategic Goal: Institutionalize Implementation of the Homeless Plan
Objective | Strategy | Time Frame | Lead Entity
1. Provide staff resources to develop Homeless plan | Assign Deputy Commissioner for Disability and Income Security Programs (DCDISP) as Agency lead for plan development. | 02/02 | DCDISP
| Establish an intercomponent workgroup | ongoing | DCDISP
2. Continue/expand participation in the Interagency Council on Homelessness | Participate in meetings | ongoing | DC or designee
3. Develop Plan | Identify homeless activities, identify barriers the homeless face in accessing SSA programs | 08/02 | Workgroup
| Prepare and submit status report | 09/30/02 | DCDISP
| Analyze policy proposals, whether legislative, regulatory or administrative that may effect the homeless. | annually | DCDISP
4. Publicize SSA's Homeless Plan | Prepare Commissioner's Broadcast, provide homeless plan on SSA's website, establish link on SSA's webpage for homeless advocates, release EM to field offices, alert Regional Communication Directors of publicity efforts. | 12/02 | Workgroup, DCO, and DCOMM
II. Strategic Goal: Improve data collection, analysis and dissemination for the homeless.
1. Collect info/data on homeless populations | Identify locations of high homeless populations through local FOs and Public Affairs Specialists | 10/02 | DCO
| Request data from Office of Systems on transient indicator on MSSICS and SSR "remarks" field | 10/02 | Workgroup
| Obtain census data to augment FO data. | 11/02 | OP
| Share information with SSA components, FOs and regions to determine which areas to target | 12/02 | Workgroup
| Target efforts and design a modest data collection method to aid the assessment of homeless initiative. | ongoing | OP
2. Inventory current practices and methods to serve the homeless | Obtain info from SSA regional offices and DDSs on best practices with mental health/social services agencies; provide results | 2/03 | Workgroup
III. Strategic Goal: Ensure accesss and services to the Homeless
1. Research current relevant policies on service to the homeless | Research FOs, DDS, OHA instructions and policies and check them for consistency; examine the results of previous outreach demonstration projects | 12/02 | DCDISP
2. Address service delivery issues through collaborations and internal measures | Establish partnerships to support homelessness activities (with advocates, organizations, third party grantees and governmental agencies - DOJ, DHHS, DOL, Health Care for the Homeless, etc.) | ongoing | Workgroup
| Provide assistance in completing SSA applications and forms and obtaining basic proofs/evidence to process claims from homeless persons; expedite processing of homeless claims | ongoing | DCO
| Encourage FO's to use, and expand where appropriate, SSI prerelease applications; Remind DDS's to obtain all medical records prior to scheduling CE's for homeless applicants. | 06/03 | DCDISP
| Continue the Mental Health Advocacy Project (Baltimore) that provides presumptive eligibility for homeless individuals whose primary provider alleges they are eligible. | ongoing | DCDISP
3. Maximize use of media that target homeless populations | Provide input/support to appropriate staff, recommend strategies for communicating with homeless through community-based organizations, shelters, etc. | ongoing | Workgroup
4. Review and improve where necessary the representative payee system for the homeless recipients and beneficiaries | Implement local recruitment campaigns to increase the number of qualified representative payees | ongoing | DCDISP
5. Provide training to SSA and DDS staff to increase their ability to service the homeless. | Identify which employees need training and incorporate into ongoing training initiatives (classes, IVT, etc.) | FY 03 | DCO
6. Monitor activities in SSA's homeless plan | Request periodic component status reports | ongoing | Workgroup
7. Establish/maintain liaison with national community-based organizations/ non-profits serving the homeless | Compile list of national CBO and nonprofit organizations, consult with these groups to find ways SSA can help reach the homeless, | FY 03 | DCOMM
| Establish SSA homeless liaisons in SSA regional offices | ongoing | DCO