## Sheet1
Annual Plan Date Calculator
Annual Plan Year: | 2021
LHA Fiscal Year End: | 2020-09-30
Recommended Hearing Month: | June
Public Hearing Date:
Enter hearing date above.
Description | Recommended Date
Take AP training session | March
Complete CIP Preparation | 2020-04-02
Gather information for AP | 2020-03-31
Complete AP Draft | 2020-04-14
Post draft AP and hearing notice (46 days before hearing date). See note below. | 2020-04-16
Review draft AP with LTOs | 2020-05-18
Hold public hearing | 2020-06-01
Revise AP and obtain Board approval | 2020-07-02
Submit to DHCD (Date Due) | 2020-07-31
DHCD review | August - September
REQUIREMENT FOR POSTING HEARING NOTICE:
760 CMR 4.16(6)(b) requires that the public hearing be advertised on the LHA website, in public postings, and by contacting LTOs at least 45 calendar days before the hearing.
REQUIREMENT FOR POSTING DRAFT ANNUAL PLAN:
760 CMR 6.09(3)(h) requires that the draft Annual Plan be posted on the LHA website with a copy in the LHA office and distributed to each LTO 30 business days before the hearing. To simplify date calculations, DHCD is requiring that the draft be posted 46 calendar days before the hearing, which will always meet the 30 business days requirement. It is sufficient to post a link to the CIMS public portal (https://dhcdcims.intelligrants.com/...) rather than posting the pdf file.

## Sheet2 (hidden)
FYE
2020-03-31
2020-06-30
2020-09-30
2020-12-31